## Issues list
Item	Priority	Class	MoSCoW	Status	Difficulty est	Description	Justification	Date	Notes
1		Coding	M	delivered		Use base3 coding to classify overlaps	Simplifies the filter logic from “If..then ...elif .. elif” which was complex, hard to follow and error-prone.
2		UI	S	delivered		Add intron/exon boundary extension variable as a GUI-selectable parameter, rather than in reference data file	Improves transparency to user AND reduces data-file maintenance
3		Validation	M	delivered		Extract the same region in both + and - strand and check that a given SNP x_ref shows the same (forward) variant- sequence definition	Validating that implementation (check sequence polarity and reverse-complement when -) is consistent with Ensembl data-extraction.
4		Validation	M	In-progress		Develop test-data sets to verify that each of the overlap types are identified by the code and processed correctly	Validating that the overlap-detection algorithm works	3rd Feb 2021	Need to check that split-feature variants are correct
5		Validation	M	delivered		Test how insert/deletions are dealt with: correct position, correct CIGAR; correct SAM values	Validating the core functionality of the product
6		Validation	S	delivered		Add duplex sequencing (both strands)	Adding core functionality of the product. Likely a pre-requisite for paired-end sequencing. Wasn’t hard to add anyway
7		Coding	C	delivered		Retain Feature-list items: source & gene in the .gbout files	Consistency and commutative ability (output files are acceptable as input files)	3rd Feb 2021	a) Now retaining non_variant features in merge_seqvar_records b) In read_mutrecord, switched write_gb_features from “short” to “long”
8		Coding/validation	W	No benefit		Output of reference features: ascending variant numbers are for + , descending for -	Consistency with Genbank format as delivered by Ensembl extraction process. Also: commutative behaviour		Not necessary
9		Coding/validation	C	delivered		Work with, or just annotate, absolute genomic coordinates instead of relative, as at present	May be a significant long-term advantage in terms of user-clarity as to where the given variant lies There are many ways of implementing this: some more thorough than others.	Early March 2021
10		Performance	S/C	delivered		detect when pre-scanning of reference file is not needed	Avoids unnecessary re-reading of an input file as well as journal and readme file generation. This adds : cpu and time. Not really noticeable in Python implementation: More of an issue in Mikkel’s browser implementation: additional file downloads where the Journal version number will get out_of_synch with the results. need to detect when this isn’t needed in the close_files feature.		Solution was to use config.json file to hold key information about the input files. That way read-ahead is not needed. This became a necessity for WEB UI because the read-ahead wasn’t feasible: could not pass values back.
11		UI /validation	C	Not started	1	Modify overlap code to scan variant sets to identify incompatible combinations: Move get_mutref_olap3 outside merge_seqvar_records	Will prevent the situation where the application applies more than one “variant” to the same coordinates. This will result in incorrect / corrupted output. This could be maintained by good data curation, but that would require some code to check it, so why not include it in the application? Future features can re-use the overlap-detection code. Besides: this feature becomes obligatory if add feature to allow different variant sets can be combined
12		UI	C	delivered		Eliminate som1 … som9 and replace with all haps. Hap_0 or Hap_ref will be the no-variants reference sequence.	Might be easier to explain. Redefining this: retaining somx and going for re (no-variants), hap1 & hap2 as parentals
13		UI	C	Incomplete delivery	3	Allow selection, from a list of variant sets, which becomes “hap1” & “hap2” ie: parentals. Then allocate which parent the “somx” variants have.	A change in the way things are currently presented, providing ability to mix& match in a variety of ways. This could reduce the need for data hand-curation, but it will necessitate item11 as a pre-requisite.		Sep 2022: Partly delivered with the ‘Build” feature, for user-defined, but overlaps not filtered!
14		UI	S	delivered	3	Select from a list of transcripts in the reference sequence	Increases the scope of the “exonic sequence” capability. Rather than have to pre-set which exons are available – make them user-selectable. Will decrease data-curation overhead. Will almost certainly need to provide absolute coordinates to the user
15		Coding	M	delivered	2	Implement a configuration file for a) input/output path “constants” b) other pre-set constants c) defaults of user-selectable variables	Vastly improve the ability to manage different data sets for different user-accounts, without changing the code. Essential to minimise code-maintenance. It’s more like the way professional programs are written	9th Feb 2021
16		Coding	M	delivered		Ensure the “exome extension” actually extends the “exomic” sequence by including intron sequence, and does does not shorten it.	Fundamental correct working. Prompted by dealing with overlap case 22	5th Feb 2021
17		Coding	W	No benefit		Allow negative exome extension values – meaning that the exon is trimmed at the ends, not extended.	No obvious good reason to do this at present. Testing shows it needs changes to (python) spinvars input-verification to change. It also doesn’t appear to work !
18		Coding	S	delivered	4	Add paired-end sequencing	This was nearer difficulty 2 than 4. Not that the actual sequence -generation was hard, but tracking the position correctly in v: r: positions was. Lots of extra code and code modifications
19		Validation	M	delivered	3	Revise/add a sorting algorithm for the overlap	Pointless to have overlap detection without proper sorting: case 8 the highlighter	6th Feb 2021
19		Validation	M	delivered	4	For split or truncated overlap variants, need to trim any substituted string	Pointless to have overlap detection without proper substring substitution	4th Feb 2021
20		Coding	C	delivered		Output of reference features: x_ref.gbout : decide join/skip strategy and tidy up the many output options. Not sure they are all in use.	Tidy up and eliminate redundant code. def write_refseq and write_outref - only called by modify_refseq why do I have both? Is make_ref_varseq redundant?
21		Coding	C	Not started	1	Sorting of feature list – can this be improved?	Algorithm efficiency?
22		UI	C	Not started	4	Hyperlink from hap1 … som9 to download input file	User sees input data beforehand. Otherwise they have to do a run with “source feature tables” selected. Problem with Python GUI version: opens input file. Not good!
23		UI	C	Partial delivery	4	Run button more prominent / A message after press so user knows something is happening	User sees it, understands what happens next. Implemented in browser version
24		UI	C	Deprecated	5	Change “splice-trigger from “splice” to “exome”.Do this if do not do item 14	Splice-trigger in source file eliminated with implementation of 14
25		UI	S	delivered	2	User help, about and more pages	Page initiated. Now advanced content
26		UI	W	Not started		After Run, need something other than “...”
27		UI	C	delivered	5	Hyperlinks from output options to help-pages
28		Coding	W	delivered	4	Remove pre-scanning from Python GUI	The better way is to use preset config data, now implemented. Re-introduced for builder and join features. Need to put joins in config to obviate this. Now operates with or without. With needed for Browser version because it relies on Python error-generation to catch absence. This doesn’t work in compiled for browser version
29		Maintenance	W	delivered	4	Create means of generating the mRNA transcripts ids when processing a .gb file	Save manual processing
30		UI	S	delivered	3	Create Replicon genetics home page
31		Data curation	W	No benefit	1	Create a sarscov2 dataset	Kudos? Novelty? No longer timely
32		UI	S	delivered	5	Change all references to “skip” in Journal to “gap”	Consistency with other documentation, notably SAM definitions
33		UI	W	No benefit	4	add misc_RNAs to selectable transcripts list	The misc_RNAs are in the feature table, but currently filtered out.This accounts for missing transcripts listed in Ensembl transcripts page. They seem to be exclusively “Retained intron” or “Processed transcript”. But it’s going to need changes to skip_trigger and the .json files
34		Coding	W	No benefit	1	ref_gbout has gap features before main gene def: remove the necessity for this	Need this for gene-boundary difference from downloaded sequence. Typically a 500-base up stream and downstream extension. However this buffer is needed, to allow for boundary redefinitions as already demonstrated for at least one of the three initial test sets. It saves on re-defining the variant data after locus-data update. Furthermore this buffer is absolutely needed for paired-end sequencing, and was increased to 1000 at each end to accommodate.
35		Coding	C	delivered	5	make ref_spliced.fasta take the mRNA name
36		Coding	S	delivered	3	remove mut_xref1 from RG_exploder_process.py as this is vestigial	Prior version crashes the code if a variant file lacks a db_xref field even when this adds no value to the data
37		Data output	S	delivered	5	in pairs of 'all reads', the read names should differ	David Orr observation. Have made it >frg1_EB0001 and >frg1r_EB0001 instead of second being >frg1_r_EB0001
38		Data output	S	delivered	5	change “No search for splice definition in features because..” to “no splicing of exon boundaries because …”	Clarity
39		Data output	S	delivered	Was 2/3	See also issue 34. Modify output so the r- value refers to locus-start position, not the downloaded sequence. Need to choose whether to use 0-based or 1-based for relative positions!	See also issue 34. The actual issue is that the reference “position” in all the output is actually from the start of the downloaded sequence , not the gene locus. Potentially misleading. Would need to adopt a zero-based or one-based coordinate system.
40		UI	M	delivered	5	use "dual strand" instead of "duplex" in the menu	David Orr observation
41		Log data	S	delivered	3	Show ACTUAL % representation and DOC for each variant in log file	David Orr inspired: make it easier for users to validate the output so they can identify any outliers resulting from random selection.
42		log data	C	delivered	2	Change the message “Transcript definition of 'xxx-genomic', plus 'Exome extension' of 0 nt at each junction, implements splicing to remove…”	Need a different message to indicate gaps made when trimming to locus vs the gaps from splicing. Probably also needs a config.json and embl_filter overhaul
44		documentation	M	delivered	5	Document significant updates eg: DOC target on reference length, not lowest frequency, and the DOC calculations shown in journal. Screen shots for “Duplex reads” to be changed to “Dual-strand reads”	David Orr observation noted that DOC was incorrect. Previous assertion was that the DOC was based on lowest frequency seq, which was also incorrect. Effort level was 3 not 5
45		Data output	S	delivered	1	modify output file names to show _REF and _tem for reference and ‘template’ sequences; force output of _REF for non-genomic when save source selected; change input file from _ref to something else	Improved clarity over which file is the reference sequence – it’s not the source file, which is head and tail-clipped as part of the processing. This clipping is effectively the template on which splicing is made…
46		Coding	C	Not started	2	Put the mutfragcount into each mutrecs object instead of storing as a separate list mutfragcount. Likewise deprecate fragtallycount, mutfragcount_index. Removing min(mutfragcount) an issue. See also zero_mutfragcount(mutrecs). Check mutseqlims as well	Since changes to REFRECORD and mutrecs objects, storing calculated values in the object rather than using globals - continue this process. Will be a better presentation to people reviewing this code on handover.
47		Coding	C	Not started	3	Change journaling of output files so that the file names are those actually saved at point of writing instead of relying on code elsewhere re-creating that same name	Code handover and maintenance – there’s too much of this in the code, and it’s a maintenance time-bomb
48		log data/UI	C	Not started	2	Make “journal substitutions” constitutive; a system constant rather than user-selectable	Journal output has become longer, so adding this makes only a relatively small difference. Also allows up-front evidence of exon-positions; use spare user-selection for other features
49		log data/UI	C	Not started	3	Make output of Ns absolutes in ascending order; make exons output in low-to-high	First is easy … weel, apart from the weird – only an issue in – polarity transcripts; second – these are shown as-processed, meaning high-numbers to low numbers. Would have to cache the output and then reverse.
50		log data/UI	S	Not started	2	add the downloaded date of locus data set to the Journal file ; highlight the Ensembl transcript id version	Allow/prompt user to check current version vs …
51		Coding	W	Not started	1	Use API to grab latest locus data from a server	No more out-of-date locus ranges
52		Coding	C	delivered	3	Detect rel37 vs rel38 data sets and change url to match	Could mix v37 and v38 loci in same data release; the code is already in a good state to deliver this – doubts only over the App.vue end	01/04/23	Has crept into place for Python GUI. Completed by allowing exceptions fpr transcript ids ending in ‘m’- AK2’s MANE-Select being the prime example: lifted the definition from 38 because it’s not defined in 37; remsapped – GUI now identifies IDs ending in ‘m’ as exceptions for the template URL to point to 37. Config,json has build ID for each Locus. Corollary: data sets can be mixed.
53		data output	C	delivered	4	Retain original date and division in LOCUS line on output	Avoid the default assignment of 01-JAN-1980 and UNC to avoid distraction
54		data output	W	No benefit	4	reverse the QUAL string for rev_comp	FASTQ files of rev_comp will be wrong otherwise unless BioPython already provides for this – decided that this currently doesn’t matter
55		coding	S	delivered	4	Address bug in process.addmut	Crashes on certain data combinations eg: when AK2_EB0006 defined as a duplication instead of as an insert	01/04/23	Was due to mutfreqs not being extended – fixed independently of this list
56		validation	S	Not started	3	Check that the truncations are happening in the right place	Found late on that olaptype 6 was cutting 1 base too late. Are all other calls to addmut_del not doing -1 likewise affected? Need data set to check this out to avoid other mistakes
57		coding/UI	C	delivered	1	Add ability to process as reverse strand	Kind of a user request (David Orr) when locus data was always presented as the sense strand.. Two-step approach: changed data so it was aways in the + forward strand and then added ability to reverse-complement right from the start. It became a right can of snakes, and I nearly gave up but ultimately succeeded
58		documentation	S	delivered	4	Place documentation of overlap types into public domain github location	If the code is to have any life at all after original developer’s work, the overlap types must be documented!		Location annotated in RG_exploder_process.py
59		coding	S	Not started	4	Need to trap where (Begin + Begin_ext) is HIGHER in value than (End + End_ext) and other weird combinations.	Attempting to create a subseq from negative coordinates is either going to crash or cause puzzlement. This is fixed in App.vue by preventing entry of Begin > End. Cannot do this in python gui in current implementation
60			W			BED file of regions to cover: ie: upload BED file to define vars?	Meeting of 20-May-2022 with Eleanor, Liz, Mamoona; incomplete notes
61			W			VCF format to specify variants	Meeting of 20-May-2022 with Eleanor, Liz, Mamoona; incomplete notes
62			W			UMI’s Unique molecular identifier – don’t know what this means	Meeting of 20-May-2022 with Eleanor, Liz, Mamoona; incomplete notes
63			W			Amplicon, gene fusion	Meeting of 20-May-2022 with Eleanor, Liz, Mamoona; incomplete notes
64		coding	C			Add a “Duplicate” button in the builder section	Easier editing
65		coding	W			Remove from the saved .gbin and .gbout files the “KEYWORDS . SOURCE . ORGANISM . .” section, if possible	Messy, unneeded extra lines
66		coding	S	delivered		Fix KRAS minus data	The join data looks identical to the plus version, so I have screwed up somewhere. It was the plus data in transcripts.json for 38 that was wrong. Second issue in mapping positions for “minus”.	2nd May 2023	Must have been a manual error for the wrong data set; there was, however an incorrect absolute value calculation for KRAS_minus. Arose from setting all to +1, instead of in non-complement direction. Required modifying the offset, but this mixture overlooked.
67		coding	W			Redundancy?	Still need to check throughout for -1 combinations with is_join_complement
68		coding	S	delivered		Add paired-end exomes	Christophe Roos request June 2024
69		coding	C		4	Eliminate lottoline/lottowin and replace with random.choices	Uses Python function instead of generating a 1000-long array, and the code to generate it
70		coding	S	delivered	2	Modify pre-processing to eliminate embl_feature_filter7.py	The code is really hard to understand and maintain; a better alternative would be to re-use modules from the main processing code	5th Feb 2025	embl_feature_filter_revise.py is the solution ;embl_feature_filter8.py is an update on embl_feature_filter7.py
71		coding	W		1	Modify pre-processing to use NBCI downloads	NCBI downloads are a bit cleaner than Ensembl, but the transcript IDs & link to CDS may prevent viability. May require changes to main processing to deal with alternative formats.

## Definitions
Moscow definitions
Code	Long Code	Definition
M	Must Have	Non-negotiable product needs that are mandatory for function or team

S	Should Have	Important initiatives that add value but are not vital

C	Could Have	Nice to have initiatives that would have a small impact if left out

W	Will not have	Initiatives that are not a priority for the current time frame -”Wish list”

Class	Long Code	Definition
Coding	Coding	Improvement in the code: for maintainability of code or data-management
UI	UI	User interface: an anticipation that this is a likely user requirement or one that will demonstrate we understand what the user could want
Validation	Validation	Activity needed to show that the application is interacting with the data as expected . Without this the user or developer will have to engage in a lot of extra validation steps to be assured this is so. Eg: global mapping coordinates will be easier to cross check to a external source such as Ensembl or dbSNP
Performance	Performance	Improve speed of execution or reduce input/output requirements

Difficulty definitions
1	Very Hard	Considerable processing code change, UI development, or data-curation with likelihood of, or confidence in, success low
2	Hard	Considerable processing code change, UI development, or data-curation. Success likely
3	Medium	Modest amount of coding or data required
4	Moderate	Small amount of coding or data-curation required
5	Easy	Just do it